## Sheet1
Task number | Name | Start | Depends on | Duration (days)
1 | Input: PO Release from Sales/BD | 2023-02-27 09:00 |  | 1
2 | Input: PRA Release from Sales/BD | 2023-03-01 09:00 |  | 1
3 | Input major milestone date: CKOM | 2023-03-16 09:00 |  | 1
4 | Input major milestone date: CDRM | 2023-06-12 09:00 |  | 1
5 | Input major milestone date: TG1 | 2023-03-31 09:00 |  | 1
6 | Input major milestone date: TG2 | 2023-09-08 09:00 |  | 1
7 | Input major milestone date: Baselay | 2023-03-10 09:00 |  | 1
8 | Contractual RTS Date | 2023-04-01 09:00 |  | 1
9 | Create and update Invoice Milestones | 2023-03-10 09:00 |  | 1
10 | PD: Review Terms and Conditions | 2023-03-01 09:00 | 1 | 7
11 | PD: Review Risk Matrix | 2023-03-01 09:00 | 1 | 7
12 | PD: Review PO | 2023-03-01 09:00 | 1 | 7
13 | PD: Process time for Acknowledge PO | 2023-03-08 09:00 | 11, 12 | 7
14 | PD: Acknowledge PO | 2023-03-15 09:00 | 1, 13 | 1
15 | PRA Setup Complete Trigger for Downstream | 2023-03-03 09:00 | 1, 2 | 7
16 | PD: Process time for Baan Project Setup | 2023-03-10 09:00 | 15 | 7
17 | PD: Baan Project Setup | 2023-03-17 09:00 | 16 | 14
18 | PD: Process time for Salesforce Project Setup (includes Invoice) | 2023-03-10 09:00 | 15 | 7
19 | PD: Salesforce Project Setup (includes Invoice) | 2023-03-17 09:00 | 18 | 14
20 | PD: Process time for Set up BP code and BIM project requests | 2023-03-10 09:00 | 15 | 7
21 | PD: Set up BP code and BIM project requests | 2023-03-17 09:00 | 20 | 14
22 | PD: Process time for Set Up Folder via Audit Requirements | 2023-03-16 09:00 | 14 | 7
23 | PD: Set Up Folder via Audit Requirements | 2023-03-23 09:00 | 22 | 14
24 | PD: Process start Update SF acceptance field - Sales Engineer | 2023-03-01 09:00 | 1 | 7
25 | PD: Update SF acceptance field for Sales Engineer to be paid | 2023-03-10 09:00 | 15, 24 | 21

## Details
ProjectName | 4F14
Logo1 | C:\Users\arjun\OneDrive\Documents\UCSD\SPRING2024\Propel\Sample_Project\Shell.png
Logo2 | C:\Users\arjun\OneDrive\Documents\UCSD\SPRING2024\Propel\Sample_Project\logo_solar_turbines1.jpg
Project Full Name | 4F14 Shell E8 Mini Compression
Contract Title | Sarawak Shell Berhad Malaysia, 4513914657
Attention | Leow Seng Leong
CC | Alyssa Maiyor, Ian Weinberg, Brian Malo, Monica Vom Schemm (ITT-B)
PO/LOA Date | 2022-02-23
Contract Duration | 15 Months/17 Months (CIP)
Readiness to Ship Forecast | July 19, 2023 (To match airplane)
Contractual Delivery Date | 2023-07-23
Forecast Delivery Date | 2023-07-19
Delivery Term | Ex-works Solar Facility
Vendor/Manufacturing Location | San Diego, United States
Scope of Work | 1 x Centaur 50 - Multiphase Pump

## Progress Summary
EARLY ENGAGEMENT COMPLETE FEBRUARY 2022
INTERNAL KICK OFF MEETING / TOLLGATE 1 MEETING COMPLETE FEBRUARY 2022
CKOM MEETING COMPLETE MARCH 2022
PROJECT DRAWINGS ISSUED MAY 2022
CDRM MEETING COMPLETE JULY 2022
TG2 MEETING-COMPLETE - AUG 22, 2022
DESIGN STUDY - AT ITT-B COMPLETE - OCT 18-20, 2022
STRING TEST-COMPLETE
PROJECT SHIPPED-COMPLETE

## Areas of Concern
Shell must update PO incoterms to reflect change in transportation. - COMPLETE
Design delays have impacted project delivery, primarily for the LOS and SOS systems. Design clarifications were ongoing until June 20 causing schedule impact for ITT-B and subsequently the overall project delivery
ITT-B Pump Casing failed during the first casting pour. Re-Pour complete, fettling complete, NDT inspections in work
Current Schedule forecasted for July 19, 2023 RTS per request from Shell ship for Antonov