## Sheet1
Task number | Name | Start | Depends on | Duration (days)
1 | Input: PO Release from Sales/BD | 2023-02-27 09:00 |  | 0
2 | Input: PRA Release from Sales/BD | 2023-03-01 09:00 |  | 0
3 | Input major milestone date: CKOM | 2023-03-16 09:00 |  | 0
4 | Input major milestone date: CDRM | 2023-06-12 09:00 |  | 0
5 | Input major milestone date: TG1 | 2023-03-31 09:00 |  | 0
6 | Input major milestone date: TG2 | 2023-09-08 09:00 |  | 0
7 | Input major milestone date: Baselay | 2024-01-31 09:00 |  | 0
8 | Contractual RTS Date | 2024-04-01 09:00 |  | 0
9 | Create and update Invoice Milestones | 2022-03-10 09:00 |  | 0
10 | PD: Review Terms and Conditions / Supplementary Documents | 2023-02-28 09:00 | 1 | 7
11 | PD: Review Risk Matrix | 2023-02-28 09:00 | 1 | 7
12 | PD: Review PO | 2023-02-28 09:00 | 1 | 7
13 | PD: Process time for Acknowledge PO | 2023-03-07 09:00 | 11, 12 | 7
14 | PD: Acknowledge PO | 2023-03-14 09:00 | 1, 13 | 1
15 | PRA Setup Complete Trigger for Downstream | 2023-03-02 09:00 | 1, 2 | 7
16 | PD: Process time for Baan Project Setup | 2023-03-09 09:00 | 15 | 7
17 | PD: Baan Project Setup | 2023-03-16 09:00 | 16 | 14
18 | PD: Process time for Salesforce Project Setup (includes Invoice) | 2023-03-09 09:00 | 15 | 7
19 | PD: Salesforce Project Setup (includes Invoice) | 2023-03-16 09:00 | 18 | 14
20 | PD: Process time for Set up BP code and BIM project requests | 2023-03-09 09:00 | 15 | 7
21 | PD: Set up BP code and BIM project requests | 2023-03-16 09:00 | 20 | 14
22 | PD: Process time for Set Up Folder via Audit Requirements | 2023-03-15 09:00 | 14 | 7
23 | PD: Set Up Folder via Audit Requirements | 2023-03-22 09:00 | 22 | 14
24 | PD: Process start for Update SF acceptance field for Sales Engineer to be paid | 2023-02-28 09:00 | 1 | 7
25 | PD: Update SF acceptance field for Sales Engineer to be paid | 2023-03-09 09:00 | 15, 24 | 21
26 | PD: Process Buffer for Initiate Financial Instruments | 2023-02-28 09:00 | 1 | 7
27 | PD: Initiate Financial Instruments | 2023-03-07 09:00 | 26 | 14
28 | Invoice 1 update (based on contract) | 2023-03-14 09:00 | 26, 13 | 7
29 | Process time for Invoice 2 | 2023-03-14 09:00 | 28 | 90
30 | Invoice 2 update (based on contract) | 2023-06-12 09:00 |  | 7
31 | Invoice 3 update (based on contract) | 2024-01-31 09:00 |  | 7
32 | Invoice 4 update (based on contract) | 2024-04-01 09:00 |  | 7
33 | Invoice 5 update (based on contract) | 2023-03-09 09:00 |  | 7
34 | Invoice 6 update (based on contract) | 2023-03-09 09:00 |  | 7
35 | Invoice 7 update (based on contract) | 2023-03-09 09:00 |  | 7
36 | Invoice 8 update (based on contract) | 2023-03-09 09:00 |  | 7
37 | Invoice 9 update (based on contract) | 2023-03-09 09:00 |  | 7
38 | PD: Processing time for Maintain Change Order Log and submit as required | 2023-03-26 17:00 | 1 | 0
39 | PD: Maintain Change Order Log and submit as required | 2023-03-27 09:00 | 38 | 14
40 | PD: Monitor On time Payment Activity | 2023-02-28 09:00 | 1 | 7
41 | PD: Processing time for Internal Handover Meeting Process | 2023-03-09 09:00 | 15 | 7
42 | PD: Internal Handover Meeting Process | 2023-03-16 09:00 | 41 | 7
43 | PD: Early Engagment Call w/ Cust | 2023-03-23 09:00 | 41, 42 | 7
44 | PD: Process time for Internal Kickoff Meeting (IKOM) | 2023-03-09 09:00 | 15 | 14
45 | PD: Internal Kickoff Meeting (IKOM) | 2023-03-23 09:00 | 44 | 7
46 | PD: Supplier Kickoff with Major Suppliers (As Required) | 2023-03-23 09:00 | 42 | 21
47 | PD: Process Buffer For Hold Initial Inspection and test plan Meeting, Release ITP Rev A | 2023-03-30 09:00 | 45 | 7
48 | PD: Hold Initial Inspection and test plan Meeting, Release ITP Rev A | 2023-04-06 09:00 | 47 | 14
49 | PD: Review Drawing Supplier Drawing Register List / Release Strategy | 2023-03-23 09:00 | 42 | 7
50 | PD: Review Long Lead Items Orders vs. Schedule (Strategy / Identify) | 2023-03-23 09:00 | 42 | 7
51 | PD: Review Project Risks and Call PRR | 2023-03-30 09:00 | 50 | 14
52 | PD: Initial trigger for PRR Meeting (Cash Flow, Summary, Dashboard) | 2023-04-13 09:00 | 51 | 7
53 | PD: PRR Meeting (Cash Flow, Summary, Dashboard) | 2023-04-20 09:00 | 52 | 14
54 | PD: Initial trigger for CKOM with Customer | 2023-03-09 09:00 | 15 | 30
55 | PD: CKOM with Customer | 2023-04-08 09:00 | 54, 3 | 14
56 | PD: Initial trigger for CKOM MOM | 2023-04-22 09:00 | 55 | 7
57 | PD: CKOM MOM | 2023-04-29 09:00 | 56 | 7
58 | PD: Initial trigger for TG1 Meeting (25 M Days) | 2023-04-22 09:00 | 55 | 10
59 | PD: TG1 Meeting (25 M Days) | 2023-05-02 09:00 | 58, 5 | 7
60 | PD: Initial trigger for Transmit Drawings (Rev A drawings, Pils, ES, Datasheets, Non-Core Drawings) | 2023-05-09 09:00 | 59 | 35
61 | PD: Transmit Drawings (Rev A drawings, Pils, ES, Datasheets, Non-Core Drawings) | 2023-06-13 09:00 | 60 | 4
62 | PD: Initial trigger for Ancilliary Approvals / Supplier Quote Approvals, Release PO | 2023-04-22 09:00 | 55 | 7
63 | PD: Ancilliary Approvals / Supplier Quote Approvals, Release PO | 2023-04-29 09:00 | 62 | 14
64 | PD: Initial trigger for CDRM with Customer | 2023-05-09 09:00 | 59 | 20
65 | PD: CDRM with Customer | 2023-06-13 09:00 | 64, 4 | 7
66 | PD: HAZOP (as required) | 2023-05-09 09:00 | 59 | 14
67 | PD: Initial trigger for TG2 Meeting (15 M Days) | 2023-06-20 09:00 | 65 | 14
68 | PD: TG2 Meeting (15 M Days) | 2023-07-04 09:00 | 67 | 14
69 | PD: Initial trigger for Hold Second ITP Meeting, Release ITP Rev B | 2023-04-22 09:00 | 55 | 14
70 | PD: Hold Second ITP Meeting, Release ITP Rev B | 2023-05-06 09:00 | 69 | 7
71 | PD: Initial trigger for Transmit TG2 Drawing | 2023-07-18 09:00 | 68 | 21
72 | PD: Transmit TG2 Drawing | 2023-09-09 09:00 | 71, 6 | 4
73 | Review Readiness for Pre-Commissioning Meeting | 2023-07-18 09:00 | 68 | 1
74 | PD: Lag time for processing Line Meeting | 2023-07-19 09:00 | 73 | 90
75 | PD: Line Meeting | 2024-02-01 09:00 | 7 | 10
76 | PD: Initial trigger for Verify ship ahead items | 2023-04-22 09:00 | 55 | 0
77 | PD: Verify ship ahead items | 2023-06-20 09:00 | 76, 65 | 1
78 | PD: Initial trigger for Verify Spare Parts List (as required) | 2023-04-22 09:00 | 55 | 0
79 | PD: Verify Spare Parts List (as required) | 2023-06-20 09:00 | 78, 65 | 1
80 | PD: Review FAT dates, Send out notice, Pre-Test Meeting | 2023-06-21 09:00 | 79 | 7
81 | PD: Lag time for Review FAT dates, Send out notice, Pre-Test Meeting (Proxy Task) | 2023-06-28 09:00 | 80 | 6
82 | PD: Lag time for PDRM | 2023-07-04 09:00 | 81 | 90
83 | PD: PDRM | 2023-10-02 09:00 | 82 | 10
84 | PD: Pre-Cash Meeting | 2023-10-12 09:00 | 83 | 10
85 | Lag time for Pre-Cash Meeting (Proxy Task) | 2023-10-22 09:00 | 84 | 10
86 | PD: Realized Baselay- Check CIMS for Payment Received | 2024-02-01 09:00 | 54, 7 | 7
87 | PD: Initial trigger for Package Assembly Commencement | 2024-02-08 09:00 | 86 | 1
88 | PD: Package Assembly Commencement | 2024-02-09 09:00 | 87 | 1
89 | PD: Initial trigger for Package Test Commencement | 2024-02-08 09:00 | 86 | 9
90 | PD: Package Test Commencement | 2024-02-17 09:00 | 89 | 6
91 | PD: Initial trigger for Package Final | 2024-02-08 09:00 | 86 | 28
92 | PD: Package Final | 2024-03-07 09:00 | 91 | 8
93 | Final Check CIMS for Payment Received Status | 2024-02-08 09:00 | 86 | 30
94 | PD: Financial instruments before shipment? PPS? | 2024-03-09 09:00 | 93 | 2
95 | PD: Lag time for Financial instruments before shipment? PPS? (Proxy Task) | 2024-03-11 09:00 | 94 | 8
96 | PD: Lag time for Treasury Approval (Proxy Task) | 2024-03-15 09:00 | 92 | 14
97 | PD: Treasury Approval | 2024-03-29 09:00 | 86, 92, 96 | 1
98 | PD: Incoterm Met in Salesforce | 2024-03-29 09:00 | 96 | 14
99 | PD: Written notice for Readiness to Ship (send to internal groups as well) | 2024-04-02 09:00 | 8 | 0
100 | PD: Shipping (as required per incoterm) | 2024-04-12 09:00 | 98 | 7
101 | PD: Pre-Commissioning Meeting | 2024-04-02 09:00 | 99 | 42
102 | PD: As-Shipped Drawings, Start Clock | 2024-04-02 09:00 | 99 | 7
103 | PD: Review ACS for QADB/OMI hard copies, Qty and where to send | 2024-04-02 09:00 | 99 | 21
104 | PD: Initial trigger for Operation Maintenance Instruction Release | 2024-04-02 09:00 | 99 | 28
105 | PD: Operation Maintenance Instruction Release | 2024-04-30 09:00 | 104 | 14
106 | PD: Initial trigger for QA Databook, Reach out to Team | 2024-04-02 09:00 | 99 | 70
107 | PD: QA Databook, Reach out to Team | 2024-06-11 09:00 | 106 | 21